## CrewSignal Deployment Tracker
CrewSignal Deployment Tracker
Task # | Phase | Technical Task | Module Layer | Complexity | Description / Scope | Status
0.1 | Phase 0 — Foundation Cleanup | Reconcile Tracker w/ Reality | DevOps / CI | Low | Mark idempotency, Twilio adapter, and API-key auth as NOT done. Plan only on what actually exists in the code. | Complete
0.2 | Phase 0 — Foundation Cleanup | Add tenacity + WAL mode | Core Engine | Low | Add tenacity to requirements.txt. Enable SQLite WAL mode (PRAGMA journal_mode=WAL) in db.py to prevent database is locked under concurrent webhook writes. | Complete
0.3 | Phase 0 — Foundation Cleanup | Verify .env never committed | Security | Low | Repo is PUBLIC on GitHub. Run: git log --all --full-history -- .env. If anything appears, rotate those keys immediately. Public git history is permanent. | Complete
1.1 | Phase 1 — Safe Webhook Core | Model Real CRM Payloads (Pydantic) | API Webhooks | Medium | Model the actual Jobber job-complete payload from their docs including the provider event ID. Garbage data 422s cleanly instead of crashing the thread. | Complete
1.2 | Phase 1 — Safe Webhook Core | Real Idempotency (dedupe) | API Webhooks | High | Before insert, look up (tenant_id, provider, provider_event_id). If found, return 202 without duplicate row or second text. Uses the duplicate status already defined. | Complete
1.3 | Phase 1 — Safe Webhook Core | API-Key Tenant Auth | Security | High | Fill the empty deps.py. Every webhook carries a secret checked against Tenant.api_key. Invalid key returns 401. Confirms tenant_id maps to a real active Tenant. | Complete
1.4 | Phase 1 — Safe Webhook Core | Build Real Twilio Adapter | Integrations | High | Implement sms_twilio.py against BaseSMSAdapter. Wrap send in tenacity exponential backoff. Mock adapter default for local dev; pick adapter by config so tests never hit Twilio. | Complete
1.5 | Phase 1 — Safe Webhook Core | Durable Queue — Kill BackgroundTasks | Core Engine | High | Webhook writes row as pending and returns 202. Separate worker loop polls pending rows, sends, updates status to sent or failed, increments retry_count, refreshes updated_at. | Complete
1.6 | Phase 1 — Safe Webhook Core | Opt-Out / STOP Handling | Integrations | Medium | TCPA legal requirement. Suppression table, check before every send, opt-out language in template. Must exist before real texts reach real customers. | Complete
1.6a | Phase 1 — Safe Webhook Core | Twilio Inbound SMS Webhook (STOP Auto-Sync) | Integrations | Medium | When a customer texts STOP directly to the Twilio number, Twilio fires an inbound SMS webhook. Build a POST /api/v1/webhooks/twilio-inbound endpoint that receives it, checks if the body is STOP, and writes the phone number to the OptOut table automatically. Without this, the carrier blocks the message (Twilio handles that) but the internal suppression table never gets updated. Also handle random inbound texts gracefully — log and ignore. Requires the public webhook URL (task 3.4) to be configured in Twilio console under the phone number inbound settings. | Complete
1.6b | Phase 1 — Safe Webhook Core | Twilio Inbound SMS — START/UNSTOP Re-Opt-In Sync | Integrations | Low | Companion to 1.6a. When a customer texts START, UNSTOP, or YES back to the Twilio number, Twilio automatically clears its own carrier-level suppression, but our internal OptOut table is never updated — so our database still thinks they are opted out even though Twilio would deliver to them again. Extend the twilio-inbound webhook to detect these keywords and delete the matching OptOut row for that tenant/phone. Keeps our internal records in sync with Twilio reality. Needed before real customers rely on opt-out/opt-in working correctly. | Pending
1.7 | Phase 1 — Safe Webhook Core | Expand Test Suite | Testing Framework | Medium | Tests: duplicate webhook no 2nd row/send; missing/invalid key 401; malformed payload 422; worker moves pending to sent; opted-out number suppressed. | Complete
2.1 | Phase 2 — Customer Research (Parallel) | Identify 15-20 Local Contractors | Operations | Low | Roofing, HVAC, electrical along the Spring Hill / Murfreesboro corridor. Note any signal of whether they already use job software. Runs DURING build phases, not after. | Parallel
2.2 | Phase 2 — Customer Research (Parallel) | 10 Research Conversations | Operations | Low | Goal is answers not closes. Ask: What do you use to track jobs? Does anyone ask for a Google review after a job? What would automating that be worth? | Complete
2.3 | Phase 2 — Customer Research (Parallel) | Capture Findings | Operations | Low | Write down real objections, real language, real price reactions. The CRM answer here OVERRIDES the Jobber assumption. This becomes your pitch — in their words. [10 of 10 DONE] #1 salon/GlossGenius: frequency cap, must sound personal, 14-day trial ask. #2 roofer: no CRM/no GBP, wants manual control over send timing, price-insensitive. #3 cold inbound caller: no software, no GBP, early stage. #4 plumber/Jobber: beta-ready, wants kill-switch to block send on bad jobs ("angry customer filter"), $99 sweet spot/$150 needs ROI proof. #5 home inspector/Spectora: wants 45-day delay timer before send (post-negotiation), same $99 ceiling, dead-deal cancel needed. #6 transmission shop/no CRM: hard disqualify — no smartphone, refuses texting; referred a gadget-friendly tire shop owner, hinting tech-comfort (not trade) may be a real segmentation line. #7 fence/deck contractor/Jobber: strongest beta candidate, offered live test jobs, wants 1-2 day delay, $150-200 is "nothing" against $15-35k jobs. #8 barber/Square: wants INSTANT send, zero delay, contradicts #4/#5/#7 — confirms timing need is real but direction depends on job type/value. Flagged repeat-customer frequency cap and named Squire as rising barber CRM. #9 junk removal/no CRM (cash/Venmo): wants Facebook link first, Google later/optional — raises whether review destination should be configurable, not Google-only. Third person (after #2, #3) to offer to pay MORE if GBP setup is bundled in. #10 drone videographer/HoneyBook+Airtable: tried and ABANDONED building this exact tool himself — quit over A2P 10DLC hell, brand/tax ID registration, carrier "Scam Likely" filtering. Gave us our positioning line verbatim: "We handle the telecom compliance so you don't have to." Wants Zapier/Make/open API instead of direct CRM webhook. Unprompted referral idea: pivot to real estate agents. FINAL PATTERNS ACROSS ALL 10: (1) Send-timing matters but direction splits by job type/value — needs per-tenant config, not one default. (2) 5 of 10 missing real infra (CRM and/or GBP) at some level. (3) 3 of 10 explicitly tried to bundle/pay for GBP setup — recurring objection, not a one-off, but Option B (self-service guide) decision holds for now. (4) Price ceiling near $150 tracks job value/volume, not trade type. (5) Jobber and Square are the two real CRM beachheads — both confirmed multiple times with hard "no manual data entry" requirement. | Parallel
3.0a | Phase 3 — First End-to-End | Provision Toll-Free Number as A2P Bridge | Integrations | Low | Buy a toll-free number (800/833/888) in Twilio and submit Toll-Free Verification — separate process from A2P 10DLC Campaign Registry, historically faster, not blocked by the local-number CTA rejections. Use this number to unblock real beta testing while local 10DLC resubmission is still pending. NOT a replacement for the local 10DLC number long-term: customer interviews (esp. #4 plumber) show a strong preference for messages that feel personal/local, not corporate/toll-free. Plan: test now on toll-free, migrate production sending to the local 10DLC number once approved, then drop or keep toll-free as backup. | Complete
3.1 | Phase 3 — First End-to-End | Twilio Sandbox Verification | Validation | Medium | First real text to your own phone through full path: webhook -> DB -> worker -> Twilio -> phone. Verify wording, link, opt-out line, and that status flips to sent. | Complete
3.2 | Phase 3 — First End-to-End | Admin CLI (manage.py) | UI Dashboard | Medium | Create a Tenant, generate a secure API key, set their review_url. Needed to onboard anyone. Keep it boring and functional. | Complete
3.3 | Phase 3 — First End-to-End | SMS Template & Review URL Customization | Core Engine | Medium | Per-tenant message_template field with {customer_name}, {business_name}, {review_url} variables. Worker renders at send time. manage.py gains --message-template and update-tenant command. | Complete
3.4 | Phase 3 — First End-to-End | Public Webhook URL (ngrok) | DevOps / Infra | Low | Install ngrok, connect authtoken, run tunnel on port 8000. Fire a test webhook through the public https URL to confirm the server is reachable from the internet. Required before any real CRM or beta client can send webhooks to CrewSignal. | Complete
4.1 | Phase 4 — Website & Legal Compliance | Register Domain (crewsignal.io or .com) | Operations | Low | Purchase domain via Cloudflare Registrar (at-cost, no markup) or Namecheap. This domain hosts the marketing site, privacy policy, and T&C. Required before Twilio A2P campaign registration can be completed. | Complete
4.2 | Phase 4 — Website & Legal Compliance | Set Up Hosting (Carrd or GitHub Pages) | Operations | Low | Carrd.co ($19/yr) is the fastest path — drag-and-drop, custom domain, HTTPS. GitHub Pages is free if you prefer code. Goal: a live URL that hosts the marketing page, privacy policy, and T&C. | Complete
4.3 | Phase 4 — Website & Legal Compliance | Write Privacy Policy (SMS-Specific) | Legal | Medium | TCPA-compliant SMS privacy policy with a dedicated SMS section covering: no selling or sharing of mobile numbers, message frequency (one per completed job), 'Message and data rates may apply' disclosure, how to opt out via STOP, how to get help via HELP, data retention and deletion policy, and contact information for support. Claude will draft this — the SMS section must be explicit and standalone, not buried in general privacy language. Twilio reviewers specifically look for mobile number handling disclosures. | Complete
4.4 | Phase 4 — Website & Legal Compliance | Write Terms & Conditions | Legal | Medium | T&C covering: what CrewSignal is and does, contractor responsibilities for customer consent, prohibited uses, limitation of liability, governing law Tennessee, cancellation policy, disclaimer on review outcomes. Claude will draft this. | Complete
4.4a | Phase 4 — Website & Legal Compliance | Write Dedicated SMS Messaging Terms Page | Legal | Medium | Create a separate /sms-terms page (or clearly labeled SMS section within T&C) covering: what kinds of messages are sent (one review request per completed job), expected message frequency, 'Message and data rates may apply', how to opt out (Reply STOP), how to get help (Reply HELP), and customer support contact (hello@crewsignal.io). ChatGPT, Gemini, and Claude all flagged this as expected for compliant SMS programs and will make future A2P reviews smoother. Claude will write this page. | Complete
4.5 | Phase 4 — Website & Legal Compliance | Host Privacy Policy & T&C as Live URLs | Operations | Low | Publish privacy policy and T&C as live publicly accessible pages. Example: crewsignal.io/privacy and crewsignal.io/terms. Test both URLs in incognito before submitting to Twilio. | Complete
4.6 | Phase 4 — Website & Legal Compliance | Complete Twilio A2P Campaign Registration | Operations | Medium | Return to Twilio A2P Campaign form. Fill in privacy policy URL, T&C URL, and sample embedded link. Submit for carrier review. Approval takes 1-5 business days. Gives (629) 289-1997 full carrier trust. | Complete
4.7 | Phase 4 — Website & Legal Compliance | Set Up Professional Email | Operations | Low | Create hello@crewsignal.io via Google Workspace ($6/mo) or Zoho Mail (free). Required for Twilio compliance profile, client onboarding, and support. Do not use personal Gmail for business. | Complete
4.8 | Phase 4 — Website & Legal Compliance | Write All Website Copy | Marketing | Medium | Headline, subheadline, how-it-works, features, pricing tier descriptions, FAQ (8-10 questions), footer copy. Must speak to both contractor and salon verticals. Lead with outcomes not technology. Claude will write all copy. | Complete
4.9 | Phase 4 — Website & Legal Compliance | Design & Build Marketing Homepage | Marketing | High | One-page site: headline + CTA above fold, How It Works (3 steps), Who It's For (contractors + salons), Pricing (3 tiers), Social Proof placeholder, FAQ, Footer with explicit links to Privacy Policy and Terms. Footer links are required — Twilio reviewers check that privacy and terms are accessible from the main site. Claude will design and build the full HTML/CSS page. | Complete
4.10 | Phase 4 — Website & Legal Compliance | Add Contact / Demo Request Form | Marketing | Low | Simple contact form for contractors to request a demo. Use Tally.so (free) or Typeform. Submissions go to professional email. This is your inbound lead capture before a full sales process. | Complete
4.11 | Phase 4 — Website & Legal Compliance | Add SMS Consent Language to Onboarding | Legal | Medium | Add required acknowledgment to tenant onboarding confirming the contractor's customers have provided phone numbers and consent to service communications. Document this in the T&C. | Complete
4.12 | Phase 4 — Website & Legal Compliance | Form Tennessee LLC | Legal | Medium | File Articles of Organization with Tennessee Secretary of State (~$300). Obtain EIN from IRS (free, online, 10 minutes). Open business checking account. Update Twilio compliance profile from Individual to Business once formed. | In Progress
4.13 | Phase 4 — Website & Legal Compliance | Update All Registrations to LLC | Legal | Low | Once LLC is formed: update Twilio account to CrewSignal LLC, update domain registrar, update email signature, open business bank account. Keep personal and business finances completely separate from day one. | Pending
4.13a | Phase 4 — Website & Legal Compliance | Attorney Review of Legal Documents (post-revenue) | Legal | Low | Once CrewSignal has meaningful revenue (suggested threshold: first $5,000 MRR or first enterprise client), have a Tennessee business attorney review the privacy policy, T&C, and SMS messaging terms. Policy generators are appropriate for pre-revenue stage but attorney-reviewed documents provide stronger protection as the business grows. Budget $500-1,500 for this review. Not urgent now — flag for revisit at first paying client milestone. | Pending
4.14 | Phase 4 — Website & Legal Compliance | Final Compliance Review Before First Client | Legal | Medium | Before onboarding any paying client confirm: A2P campaign approved, privacy policy and T&C live, opt-out tested end-to-end, professional email set up, LLC formed or in process. Legal go/no-go gate. | Pending
5.0 | Phase 5 — Beta Validation | Lightweight Failure Alerting (Pre-Beta) | DevOps / Infra | Low | Minimal version of 6.4, pulled forward because it protects the very first real beta test. A simple Slack or email webhook that fires when a send fails or the worker stalls. Does not need structured logging or Postgres — just a single alert path so a silent failure at 2am does not go unnoticed for days during your first live client test. Full observability (6.4) still happens later at scale. | Complete
5.1 | Phase 5 — Beta Validation | Onboard 1-3 Free Beta Clients | Operations | Medium | Pulled from Phase 2 conversations. Free for honest feedback plus case study and testimonial if it works. Set expectations: early, hands-on, fast fixes. | Pending
5.2 | Phase 5 — Beta Validation | Watch It Run on Real Jobs | Validation | Medium | Monitor every send. Did it fire? Right timing? Duplicates caught? Anyone opt out? This is where you find the bugs no test predicted. | Pending
5.3 | Phase 5 — Beta Validation | Get One Piece of Proof | Marketing | Low | One contractor saying we got more reviews or this saved time. Or one screenshot of a review from a CrewSignal text. This proof sells client #2. | Pending
6.1 | Phase 6 — Harden for Paid | Migrate to Managed Postgres | Database | Medium | Trigger: first paying client. Render or Railway (~$7/mo). Change connection string, run migrations. Real money means data you cannot lose. | Pending
6.2 | Phase 6 — Harden for Paid | Alembic Migrations | Database | Medium | Set up before you have schema you are afraid to change. After this, never hand-edit DB shape again. | Pending
6.3 | Phase 6 — Harden for Paid | Containerize + Deploy (Docker/Caddy) | DevOps / Infra | High | Fill the empty Dockerfile and Caddyfile. Caddy auto-HTTPS via Let's Encrypt. Deploy to a real host with a proper domain. | Pending
6.4 | Phase 6 — Harden for Paid | Telemetry & Failure Alerts | DevOps / Infra | Medium | Structured logging (logger.py is empty) plus Slack or email alert when a send fails or the worker stalls. Know about failures before your customer does. | Pending
6.5 | Phase 6 — Harden for Paid | Internal Client Tracking Dashboard | Operations | Medium | Internal-only dashboard for Brandon to track active clients, tier, review counts before/after onboarding, and churn signals. Not customer-facing. Build once spreadsheet tracking becomes insufficient at scale. | Pending
7.1 | Phase 7 — First Dollar & Scale | Convert Beta Client to Paid | Operations | Medium | Use your proof. Start with one tier — likely $995 setup / $199/mo. The setup fee qualifies serious buyers and funds your time. | Pending
7.2 | Phase 7 — First Dollar & Scale | Record the Loom Pitch | Marketing | Low | NOW it is worth doing — scripted from real objections (Phase 2) and backed by real proof (Phase 5). 2-minute screen-share audit pitch. | Pending
7.3 | Phase 7 — First Dollar & Scale | Scale Outreach | Operations | Medium | Use findings from Phase 2 conversations plus the Loom pitch to systematically reach out to the contractor list. Goal: 10 paying clients. | Pending
7.4 | Phase 7 — First Dollar & Scale | Multi-Location Support | Core Engine | Medium | Per-location review attribution and message routing for multi-location clients. Required to actually deliver the Multi-Location pricing tier already sold at $999 setup / $299/mo. Trigger: first multi-location client signs. | Pending
7.5 | Phase 7 — First Dollar & Scale | Add Second CRM Integration (Housecall Pro or JobNimbus) | Integrations | High | Expand beyond Jobber based on Phase 2 findings — Housecall Pro and JobNimbus identified as the next most common CRMs among Middle Tennessee contractors. Pick whichever shows up most in outreach once scaling. | Pending
8.1 | Phase 8 — Square Integration | Square Developer App Setup | Integrations | Low | Create Square Developer account and app at developer.squareup.com. Obtain App ID and OAuth credentials. Enable Bookings API and Webhooks. Register CrewSignal webhook URL for payment.completed events. | Pending
8.2 | Phase 8 — Square Integration | Model Square Webhook Payload (Pydantic) | API Webhooks | Medium | Model the real Square payment.completed webhook payload. Key fields: event_id for idempotency, merchant_id maps to tenant, customer_id to look up phone via Customers API. | Pending
8.3 | Phase 8 — Square Integration | Square Customers API Lookup | Integrations | Medium | After payment.completed fires, use Square Customers API to fetch customer phone via customer_id. Store Square OAuth token per tenant. Handle customers with no phone gracefully — log and skip. | Pending
8.4 | Phase 8 — Square Integration | Square Webhook Endpoint | API Webhooks | High | Add POST /api/v1/webhooks/square-payment-completed. Validate Square webhook signature. Idempotency on (tenant_id, square, event_id). Write pending campaign row and return 202. Reuse existing worker. | Pending
8.5 | Phase 8 — Square Integration | Square OAuth Flow (per tenant) | Security | High | Each salon connects their Square account via OAuth. Build authorize and callback endpoints. Store access_token and merchant_id per tenant. Required for the Customers API lookup in 8.3. | Pending
8.6 | Phase 8 — Square Integration | Sandbox Test — Wife's Salon | Validation | Medium | End-to-end test using Square sandbox. Book a test appointment, complete a test payment, verify webhook fires, customer lookup succeeds, and a real SMS arrives. Wife's salon is first real production client after sandbox passes. | Pending
8.7 | Phase 8 — Square Integration | Expand Tests for Square | Testing Framework | Medium | Tests: valid Square payment webhook creates pending campaign; duplicate Square event_id suppressed; missing customer phone skipped gracefully; invalid Square signature returns 401. | Pending
FLAG-1 | Future Consideration — Not Yet Scoped | Configurable Send-Timing (Instant / Delay / Kill-Switch) | Core Engine | Medium | Upgraded from earlier delay-only framing after interview #8 (barber/Square) explicitly wanted INSTANT send and rejected any delay, directly contradicting #5/#7 wanting delay and #4 wanting a kill-switch. Confirmed via 4 of 8 interviews that timing matters, but the right default is NOT universal — it splits by job type/value. Real shape of this feature: a per-tenant timing setting (instant default vs. configurable delay window), possibly plus a manual hold/cancel for a specific job. NOT yet committed to a phase or build spec — needs the remaining 2 interviews to see if the split holds, then a real scoping conversation before touching code. | Pending
FLAG-2 | Future Consideration — Not Yet Scoped | Configurable Review Destination (Google vs. Facebook) | Core Engine | Medium | Flagged from interview #9 (junk removal): wants the review link to point at Facebook now, with the option to switch to Google later once GBP is set up. Raises whether review destination should be a per-tenant setting rather than Google-only. NOT committed — only one interview raised this directly; watch for repetition before deciding. Risk: expands product scope beyond "automated Google reviews." | Pending
FLAG-3 | Future Consideration — Not Yet Scoped | Generic Webhook / Zapier-Make Integration Path | Integrations | Medium | Flagged from interview #10 (drone videographer, HoneyBook+Airtable): wants Zapier/Make/open API instead of a bespoke CRM integration, since his tech stack is custom. Could open the door to solo operators on non-mainstream tools without building a 1-off integration per CRM. NOT committed — evaluate after Jobber/Square integrations are proven and Phase 2 learnings are fully digested. | Pending
FLAG-4 | Future Consideration — Not Yet Scoped | Client-Facing Send Log / Proof of Delivery | Operations | Medium | Raised during a high-tech-contractor gut-check review: a skeptical/technical client (e.g. interview #10, the drone videographer) will want to see proof texts actually went out and to whom, not just trust the system worked. Distinct from 6.5 (internal ops dashboard) — this is client-facing, even if minimal (e.g. a simple per-tenant send history view or weekly summary email). NOT committed — evaluate after first beta client raises it for real, or proactively before onboarding a technically skeptical client. | Pending
FLAG-5 | Future Consideration — Not Yet Scoped | Data Retention / Shutdown Policy for Customer Phone Numbers | Legal | Low | Raised during a high-tech-contractor gut-check review: a beta client handing over real customer PII (names, phone numbers) may reasonably ask what happens to that data if CrewSignal shuts down or a client cancels. Needs a clear, honest answer before onboarding skeptical clients — likely a short addition to Privacy Policy (data retention/deletion on cancellation) rather than new engineering. NOT committed — fold into 4.14 (Final Compliance Review) or address directly in Privacy Policy when convenient. | Pending
FLAG-6 | Future Consideration — Not Yet Scoped | Review Content Quality as AI-Visibility Lever | Core Engine | Medium | Raised while researching whether reviews affect AI recommendation engines (ChatGPT, Gemini, AI Overviews), not just Google Maps ranking. Confirmed: AI weighs review sentiment and specific keyword content (e.g. mentioning the actual service performed), not just review count or star rating — so a more descriptive review may carry more AI-visibility value than a generic one. Reviews are only one input among several or AI recommendation (entity recognition, authoritative list mentions, awards also matter), so this is a meaningful but partial lever, not a silver bullet. NOT committed — explicitly deprioritized until Phase 5+ (real paying clients exist). HARD ETHICS GUARDRAIL: any future feature here must help a genuinely happy customer recall real specifics (what was done, where) — it must NEVER suggest wording, script sentiment, or nudge reviews toward specific claims the customer did not actually make. That crosses into review manipulation, which risks Google penalties against CLIENT profiles, not just CrewSignal. Defensible version only: a gentle prompt like “mention what we did and where it happened,” nothing scripted. | Pending